## HOME
STR-02 — CONTEXT-SENSITIVE SITUATION ANALYSIS
Select the context first. STR-02 will then ask 10 universal questions plus 10 questions specific to that context.
Subject / Entity |  |  | Assessment Items | 20
Plan / Initiative |  |  | Ratings Entered | 0
Current Location / Community |  |  | Evidence Upgraded | 0
Responsible Body / Owner |  |  | Automatic Key Findings | 0
Operator / Lead Organisation |  |  | Baselines Entered | 0
Current Notes |  |  | Quick Assessment | 0 / 20
CONTEXT SETUP — CHOOSE BEFORE ENTERING ASSESSMENT DATA
Context Type | Sport Programme / Project |  | Question Set | 10 Core + 10 Sport Programme / Project questions
Assessment Stage | Reactivation / Recovery |  | Minimum Input | Rating only
Assessment Purpose | Situation Analysis |  | Context Change Rule | If context changes after data entry, review/clear the yellow response cells.
QUICK START
1 | Choose Context | Select Context Type first. Stage and Purpose frame how you interpret the questions.
2 | Quick Assessment | Select one Rating for each of the 20 questions. Confidence starts at Unverified.
3 | Add Evidence as Needed | Upgrade confidence and add evidence/source only for important or uncertain items.
4 | Review Outputs | Key Findings and Dashboard are automatic. Data Check is optional depth before STR-04.
RATING GUIDE — WHAT THE DROPDOWNS MEAN
Rating | Meaning | Use when... |  | Evidence Confidence | Meaning | Typical basis
Strong | Working well / clearly in place | Evidence shows the condition is effective and reliable. |  | High | Documented / verified | Official record, inspection, current data
Adequate | Acceptable but improvable | The condition is basically sufficient. |  | Medium | Credible but incomplete | Reliable report, partial documentation
Developing | Partly in place | Some elements exist but important work remains. |  | Low | Informed judgement | Experience or stakeholder view
Weak | Significant gap | The gap is affecting performance or readiness. |  | Unverified | Default until checked | No reliable evidence has been entered yet
Critical | Absent / blocking | The issue can prevent safe, lawful or effective implementation.
Unknown | Not enough information | You cannot yet make a responsible judgement.
Important: Context Type changes the 10 context-specific questions and the Data Check indicators. Select it before entering yellow-cell responses.

## Situation Assessment
STR-02 — CONTEXT-SENSITIVE SITUATION ASSESSMENT
Context: Sport Programme / Project ¦ Stage: Reactivation / Recovery ¦ QUICK MODE = select Rating only. Evidence Confidence defaults to Unverified and can be upgraded as evidence is added.
ID | Set | Domain | Essential question | Current situation / evidence | Rating | Evidence confidence | Source / reference | Suggested next check | Planning implication
CORE-01 | Core | Purpose and mandate | Is the purpose, mandate or intended role clear and understood? |  |  | Unverified |  | Confirm the governing mandate, agreed purpose or approved objective. | Clarify what the entity or initiative is expected to achieve before setting strategy.
CORE-02 | Core | Governance and accountability | Are decision rights, responsibilities and accountability clearly assigned? |  |  | Unverified |  | Confirm who decides, who delivers and who reports. | Unclear accountability will weaken implementation even where resources exist.
CORE-03 | Core | Leadership | Is there sufficient leadership or sponsorship to make decisions and remove barriers? |  |  | Unverified |  | Identify the accountable leader or sponsor and confirm authority. | A credible decision-maker or sponsor is needed to move issues that sit outside operational control.
CORE-04 | Core | People and capability | Are enough people with the required skills and capacity available? |  |  | Unverified |  | Identify the minimum roles and the most important capability gaps. | People and capability must match the minimum operating model.
CORE-05 | Core | Resources and finance | Are the minimum resources and funding needs understood and realistically available? |  |  | Unverified |  | Confirm essential costs, available resources and the immediate funding gap. | Strategy should distinguish essential resources from desirable additions.
CORE-06 | Core | Operations and systems | Are the essential operating processes, records and controls workable? |  |  | Unverified |  | Identify the small number of processes and records required for reliable delivery. | Only essential systems should be introduced first; unnecessary administration should be avoided.
CORE-07 | Core | Stakeholders and legitimacy | Are the key stakeholders sufficiently engaged, represented and supportive? |  |  | Unverified |  | Map the stakeholders whose support, permission or participation is essential. | Stakeholder legitimacy can enable or block implementation regardless of technical quality.
CORE-08 | Core | Demand and service need | Is the need or demand for the service, programme or activity sufficiently understood? |  |  | Unverified |  | Verify demand using the simplest credible evidence available. | Programme and resource choices should be based on demonstrated need rather than assumption.
CORE-09 | Core | Risk and compliance | Are the major legal, safety, integrity and compliance risks understood and controlled? |  |  | Unverified |  | Create one short register of non-negotiable approvals and high-consequence risks. | Critical risks should be treated as implementation gates rather than ordinary improvement actions.
CORE-10 | Core | Evidence and learning | Is enough reliable information available to monitor performance and make decisions? |  |  | Unverified |  | Identify the few measures that will show whether the situation is improving. | Data collection should be proportionate and directly linked to decisions.
PRG-01 | Context | Outcomes and target group | Are the intended outcomes and target participants clearly defined? |  |  | Unverified |  | Confirm who the programme is for and what should change as a result. | Delivery and evaluation should be organised around a small number of clear outcomes.
PRG-02 | Context | Delivery model | Is the delivery model practical for the available time, locations and participants? |  |  | Unverified |  | Review frequency, duration, locations and delivery method. | A realistic delivery model is more important than an ambitious but unworkable design.
PRG-03 | Context | Reach and participation | Is the programme reaching the intended number and type of participants? |  |  | Unverified |  | Compare target and actual participation and identify access barriers. | Low reach or the wrong participant mix should trigger redesign before expansion.
PRG-04 | Context | Delivery workforce | Are enough capable staff, coaches or facilitators available? |  |  | Unverified |  | Confirm roles, workload, technical capability and supervision. | Programme scale should reflect the real delivery workforce.
PRG-05 | Context | Venues and equipment | Are venues and equipment adequate, safe and accessible for delivery? |  |  | Unverified |  | Check venue availability, equipment gaps and safety requirements. | Delivery quality depends on reliable access to essential physical resources.
PRG-06 | Context | Budget and cost | Is the programme affordable and are the major costs understood? |  |  | Unverified |  | Compare essential costs with confirmed funding and in-kind support. | A minimum viable delivery model should be clear before adding optional costs.
PRG-07 | Context | Partners | Are the right organisations contributing participants, expertise, venues or funding? |  |  | Unverified |  | Clarify partner roles and commitments. | Partnerships should reduce delivery gaps rather than create coordination burden.
PRG-08 | Context | Inclusion and safeguarding | Is participation safe, inclusive and appropriate for the target group? |  |  | Unverified |  | Check safeguarding, accessibility, gender and cultural barriers. | Participation outcomes are weakened when access or safety barriers are ignored.
PRG-09 | Context | Monitoring and evaluation | Are outputs and outcomes being measured simply and consistently? |  |  | Unverified |  | Select a small set of measures and establish baseline and review points. | Monitoring should support decisions, not become a separate administrative project.
PRG-10 | Context | Sustainability and scale | Is there a realistic pathway to continue, improve or scale the programme? |  |  | Unverified |  | Identify what must be sustained and what evidence would justify expansion. | Scale should follow demonstrated value and delivery capacity.

## Data Check
STR-02 — CONTEXT-SENSITIVE DATA CHECK
Optional depth for Sport Programme / Project. Enter only what is known or easy to collect. If context changes, review the yellow baseline/source/quality cells.
ID | Area | Indicator | Current baseline | Unit | Source / date | Data quality | Suggested next collection action
PD-01 | Reach | Target participants |  | Number |  | Not available | Confirm current approved target.
PD-02 | Reach | Participants enrolled / reached |  | Number |  | Not available | Maintain current participant register.
PD-03 | Delivery | Planned sessions / activities completed |  | % |  | Not available | Compare planned and delivered sessions.
PD-04 | People | Active delivery staff / coaches |  | Number |  | Not available | Confirm current delivery roster.
PD-05 | Locations | Active delivery locations |  | Number |  | Not available | Confirm venue access and activity status.
PD-06 | Finance | Approved programme budget |  | Currency |  | Not available | Confirm approved budget and remaining funds.
PD-07 | Partnerships | Active delivery partners |  | Number |  | Not available | Record partner role and contribution.
PD-08 | Attendance | Average attendance / retention |  | % |  | Not available | Track participation consistency.
PD-09 | Outputs | Planned outputs completed |  | % |  | Not available | Update simple output tracker.
PD-10 | Monitoring | Required monitoring / evaluation reports completed |  | % |  | Not available | Confirm review points and reporting dates.

## Key Findings
STR-02 — AUTOMATIC KEY FINDINGS
Top eight attention items for Sport Programme / Project. These are generated automatically from the current assessment ratings and evidence confidence.
Priority | ID | Domain | Finding / current situation | Rating | Evidence confidence | Planning implication | Next verification
1 | CORE-01 | Purpose and mandate | Is the purpose, mandate or intended role clear and understood? | 0 | Unverified | Clarify what the entity or initiative is expected to achieve before setting strategy. | Confirm the governing mandate, agreed purpose or approved objective.
2 | CORE-02 | Governance and accountability | Are decision rights, responsibilities and accountability clearly assigned? | 0 | Unverified | Unclear accountability will weaken implementation even where resources exist. | Confirm who decides, who delivers and who reports.
3 | CORE-03 | Leadership | Is there sufficient leadership or sponsorship to make decisions and remove barriers? | 0 | Unverified | A credible decision-maker or sponsor is needed to move issues that sit outside operational control. | Identify the accountable leader or sponsor and confirm authority.
4 | CORE-04 | People and capability | Are enough people with the required skills and capacity available? | 0 | Unverified | People and capability must match the minimum operating model. | Identify the minimum roles and the most important capability gaps.
5 | CORE-05 | Resources and finance | Are the minimum resources and funding needs understood and realistically available? | 0 | Unverified | Strategy should distinguish essential resources from desirable additions. | Confirm essential costs, available resources and the immediate funding gap.
6 | CORE-06 | Operations and systems | Are the essential operating processes, records and controls workable? | 0 | Unverified | Only essential systems should be introduced first; unnecessary administration should be avoided. | Identify the small number of processes and records required for reliable delivery.
7 | CORE-07 | Stakeholders and legitimacy | Are the key stakeholders sufficiently engaged, represented and supportive? | 0 | Unverified | Stakeholder legitimacy can enable or block implementation regardless of technical quality. | Map the stakeholders whose support, permission or participation is essential.
8 | CORE-08 | Demand and service need | Is the need or demand for the service, programme or activity sufficiently understood? | 0 | Unverified | Programme and resource choices should be based on demonstrated need rather than assumption. | Verify demand using the simplest credible evidence available.

## Dashboard
STR-02 — CONTEXT-SENSITIVE SITUATION DASHBOARD
Context: Sport Programme / Project ¦ Stage: Reactivation / Recovery ¦ Purpose: Situation Analysis
Assessment items | 20 | Context Type | Sport Programme / Project
Ratings entered | 0 | Assessment Stage | Reactivation / Recovery
Evidence upgraded | 0 | Assessment Purpose | Situation Analysis
Quick assessment | 0 / 20 | Data indicators | 10
Weak / critical items | 0 | Baselines entered | 0
Unknown ratings | 0 | Reliable baselines | 0
Automatic key findings | 0 | Unverified confidence | 20
CURRENT PICTURE — GENERATED FROM THE TOP FINDINGS
1 | Purpose and mandate: Is the purpose, mandate or intended role clear and understood?
2 | Governance and accountability: Are decision rights, responsibilities and accountability clearly assigned?
3 | Leadership: Is there sufficient leadership or sponsorship to make decisions and remove barriers?
4 | People and capability: Are enough people with the required skills and capacity available?
5 | Resources and finance: Are the minimum resources and funding needs understood and realistically available?
READINESS TO MOVE TO SWOT
Complete the 20 Ratings first. Evidence can be added progressively.
HOW TO READ THIS DASHBOARD
• | High attention does not automatically mean highest strategic priority; it means the issue deserves explicit review.
• | Low confidence increases attention because important assumptions should be verified.
• | STR-04 should decide the strategic response. STR-02 establishes the current situation and evidence base.

## Automation
TECHNICAL AUTOMATION — NO USER INPUT REQUIRED
Ranks all 20 active questions using condition severity plus evidence uncertainty. The top eight feed Key Findings automatically.
ID | Set | Domain | Finding / current situation | Rating | Confidence | Attention score | Rank | Strategic significance | Planning implication | Next verification
CORE-01 | Core | Purpose and mandate | Is the purpose, mandate or intended role clear and understood? | 0 | Unverified | 1 | 1 | Low | Clarify what the entity or initiative is expected to achieve before setting strategy. | Confirm the governing mandate, agreed purpose or approved objective.
CORE-02 | Core | Governance and accountability | Are decision rights, responsibilities and accountability clearly assigned? | 0 | Unverified | 1 | 2 | Low | Unclear accountability will weaken implementation even where resources exist. | Confirm who decides, who delivers and who reports.
CORE-03 | Core | Leadership | Is there sufficient leadership or sponsorship to make decisions and remove barriers? | 0 | Unverified | 1 | 3 | Low | A credible decision-maker or sponsor is needed to move issues that sit outside operational control. | Identify the accountable leader or sponsor and confirm authority.
CORE-04 | Core | People and capability | Are enough people with the required skills and capacity available? | 0 | Unverified | 1 | 4 | Low | People and capability must match the minimum operating model. | Identify the minimum roles and the most important capability gaps.
CORE-05 | Core | Resources and finance | Are the minimum resources and funding needs understood and realistically available? | 0 | Unverified | 1 | 5 | Low | Strategy should distinguish essential resources from desirable additions. | Confirm essential costs, available resources and the immediate funding gap.
CORE-06 | Core | Operations and systems | Are the essential operating processes, records and controls workable? | 0 | Unverified | 1 | 6 | Low | Only essential systems should be introduced first; unnecessary administration should be avoided. | Identify the small number of processes and records required for reliable delivery.
CORE-07 | Core | Stakeholders and legitimacy | Are the key stakeholders sufficiently engaged, represented and supportive? | 0 | Unverified | 1 | 7 | Low | Stakeholder legitimacy can enable or block implementation regardless of technical quality. | Map the stakeholders whose support, permission or participation is essential.
CORE-08 | Core | Demand and service need | Is the need or demand for the service, programme or activity sufficiently understood? | 0 | Unverified | 1 | 8 | Low | Programme and resource choices should be based on demonstrated need rather than assumption. | Verify demand using the simplest credible evidence available.
CORE-09 | Core | Risk and compliance | Are the major legal, safety, integrity and compliance risks understood and controlled? | 0 | Unverified | 1 | 9 | Low | Critical risks should be treated as implementation gates rather than ordinary improvement actions. | Create one short register of non-negotiable approvals and high-consequence risks.
CORE-10 | Core | Evidence and learning | Is enough reliable information available to monitor performance and make decisions? | 0 | Unverified | 1 | 10 | Low | Data collection should be proportionate and directly linked to decisions. | Identify the few measures that will show whether the situation is improving.
PRG-01 | Context | Outcomes and target group | Are the intended outcomes and target participants clearly defined? | 0 | Unverified | 1 | 11 | Low | Delivery and evaluation should be organised around a small number of clear outcomes. | Confirm who the programme is for and what should change as a result.
PRG-02 | Context | Delivery model | Is the delivery model practical for the available time, locations and participants? | 0 | Unverified | 1 | 12 | Low | A realistic delivery model is more important than an ambitious but unworkable design. | Review frequency, duration, locations and delivery method.
PRG-03 | Context | Reach and participation | Is the programme reaching the intended number and type of participants? | 0 | Unverified | 1 | 13 | Low | Low reach or the wrong participant mix should trigger redesign before expansion. | Compare target and actual participation and identify access barriers.
PRG-04 | Context | Delivery workforce | Are enough capable staff, coaches or facilitators available? | 0 | Unverified | 1 | 14 | Low | Programme scale should reflect the real delivery workforce. | Confirm roles, workload, technical capability and supervision.
PRG-05 | Context | Venues and equipment | Are venues and equipment adequate, safe and accessible for delivery? | 0 | Unverified | 1 | 15 | Low | Delivery quality depends on reliable access to essential physical resources. | Check venue availability, equipment gaps and safety requirements.
PRG-06 | Context | Budget and cost | Is the programme affordable and are the major costs understood? | 0 | Unverified | 1 | 16 | Low | A minimum viable delivery model should be clear before adding optional costs. | Compare essential costs with confirmed funding and in-kind support.
PRG-07 | Context | Partners | Are the right organisations contributing participants, expertise, venues or funding? | 0 | Unverified | 1 | 17 | Low | Partnerships should reduce delivery gaps rather than create coordination burden. | Clarify partner roles and commitments.
PRG-08 | Context | Inclusion and safeguarding | Is participation safe, inclusive and appropriate for the target group? | 0 | Unverified | 1 | 18 | Low | Participation outcomes are weakened when access or safety barriers are ignored. | Check safeguarding, accessibility, gender and cultural barriers.
PRG-09 | Context | Monitoring and evaluation | Are outputs and outcomes being measured simply and consistently? | 0 | Unverified | 1 | 19 | Low | Monitoring should support decisions, not become a separate administrative project. | Select a small set of measures and establish baseline and review points.
PRG-10 | Context | Sustainability and scale | Is there a realistic pathway to continue, improve or scale the programme? | 0 | Unverified | 1 | 20 | Low | Scale should follow demonstrated value and delivery capacity. | Identify what must be sustained and what evidence would justify expansion.

## Question Bank (hidden)
TECHNICAL REFERENCE — STR-02 QUESTION BANK
No user input is required on this sheet. STR-02 always asks 10 core questions plus 10 questions for the selected context.
ID | Set | Context | Domain | Essential question | Suggested next check | Planning implication | Evidence examples | Context | Start Index
CORE-01 | Core | ALL | Purpose and mandate | Is the purpose, mandate or intended role clear and understood? | Confirm the governing mandate, agreed purpose or approved objective. | Clarify what the entity or initiative is expected to achieve before setting strategy. | Legislation, constitution, policy, approved concept, terms of reference | Sport Facility | 1
CORE-02 | Core | ALL | Governance and accountability | Are decision rights, responsibilities and accountability clearly assigned? | Confirm who decides, who delivers and who reports. | Unclear accountability will weaken implementation even where resources exist. | Delegations, organisation chart, board terms, responsibility matrix | Sport Organisation / Federation | 11
CORE-03 | Core | ALL | Leadership | Is there sufficient leadership or sponsorship to make decisions and remove barriers? | Identify the accountable leader or sponsor and confirm authority. | A credible decision-maker or sponsor is needed to move issues that sit outside operational control. | Appointment, sponsor confirmation, meeting decisions, delegated authority | Community Sport Club | 21
CORE-04 | Core | ALL | People and capability | Are enough people with the required skills and capacity available? | Identify the minimum roles and the most important capability gaps. | People and capability must match the minimum operating model. | Staff list, volunteer register, capability assessment, role profiles | Government Sport Department / Agency | 31
CORE-05 | Core | ALL | Resources and finance | Are the minimum resources and funding needs understood and realistically available? | Confirm essential costs, available resources and the immediate funding gap. | Strategy should distinguish essential resources from desirable additions. | Budget, cash estimate, equipment list, funding commitments | Sport Programme / Project | 41
CORE-06 | Core | ALL | Operations and systems | Are the essential operating processes, records and controls workable? | Identify the small number of processes and records required for reliable delivery. | Only essential systems should be introduced first; unnecessary administration should be avoided. | SOPs, registers, booking systems, reporting routines, operating calendar | Event / Competition | 51
CORE-07 | Core | ALL | Stakeholders and legitimacy | Are the key stakeholders sufficiently engaged, represented and supportive? | Map the stakeholders whose support, permission or participation is essential. | Stakeholder legitimacy can enable or block implementation regardless of technical quality. | Consultation records, agreements, partner commitments, community representation | General / Other | 61
CORE-08 | Core | ALL | Demand and service need | Is the need or demand for the service, programme or activity sufficiently understood? | Verify demand using the simplest credible evidence available. | Programme and resource choices should be based on demonstrated need rather than assumption. | Participation data, enquiries, survey, waiting list, school/community demand
CORE-09 | Core | ALL | Risk and compliance | Are the major legal, safety, integrity and compliance risks understood and controlled? | Create one short register of non-negotiable approvals and high-consequence risks. | Critical risks should be treated as implementation gates rather than ordinary improvement actions. | Approval checklist, risk register, safeguarding, audit, safety or legal advice
CORE-10 | Core | ALL | Evidence and learning | Is enough reliable information available to monitor performance and make decisions? | Identify the few measures that will show whether the situation is improving. | Data collection should be proportionate and directly linked to decisions. | Baseline data, attendance, finance reports, performance measures, evaluation records
FAC-01 | Context | Sport Facility | Access and authority | Is formal authority to access, manage or operate the facility clear? | Confirm written access, operating authority and the approving officer. | Facility activation should not proceed without clear authority. | Approval letter, lease, delegation, asset record
FAC-02 | Context | Sport Facility | Physical condition | Is the physical condition of the facility sufficiently known and serviceable? | Complete a documented condition inspection and identify critical defects. | Restoration priorities should be based on verified condition, not appearance alone. | Condition report, photographs, engineering inspection
FAC-03 | Context | Sport Facility | Safety and emergency readiness | Is the facility verified safe for users, staff and events? | Confirm fire, electrical, structural, emergency and liability requirements. | Public use should be gated by documented safety clearance. | Safety inspection, fire/electrical certificate, emergency plan
FAC-04 | Context | Sport Facility | Utilities and accessibility | Are essential utilities, access and basic user amenities operational? | Check power, water, sanitation, access, lighting and disability access where relevant. | A technically sound facility still cannot operate if basic services are unavailable. | Utilities check, accessibility inspection, service records
FAC-05 | Context | Sport Facility | Equipment and assets | Is essential equipment available, usable and approved for use? | Complete an equipment inventory, condition check and use approval. | Programme scope should reflect equipment actually available and serviceable. | Asset register, inventory, condition check, custody record
FAC-06 | Context | Sport Facility | Maintenance | Is there a workable minimum maintenance system and responsibility for repairs? | Identify routine tasks, urgent backlog and responsible parties. | A simple maintenance regime is necessary to prevent rapid deterioration. | Maintenance log, defect list, maintenance budget, service contracts
FAC-07 | Context | Sport Facility | Security and protection | Are security, vandalism and asset-protection risks adequately controlled? | Verify current security arrangements and introduce immediate low-cost protection where needed. | Uncontrolled deterioration or vandalism can destroy the value of later investment. | Security assessment, incident records, guards, locks, fencing, lighting
FAC-08 | Context | Sport Facility | Space and programme suitability | Can the available spaces realistically support the intended sport and community programme? | Prepare a simple space–activity–equipment matrix. | The operating programme should be designed around usable spaces rather than wish lists. | Floor plan, space audit, sport dimensions, equipment needs
FAC-09 | Context | Sport Facility | Use and operating readiness | Are booking, opening hours, supervision and user-management arrangements workable? | Define the minimum operating day, booking method and supervision requirements. | Early activation should use simple controls that staff and users can follow. | Booking process, opening schedule, supervision plan, attendance register
FAC-10 | Context | Sport Facility | Asset custody and owner–operator relationship | Are owner, custodian and operator responsibilities for the facility and equipment clearly separated? | Agree who owns, maintains, insures, controls and reports on each asset class. | A clear owner–operator arrangement reduces disputes and protects public assets. | MOU, asset custody agreement, reporting arrangement, insurance responsibility
ORG-01 | Context | Sport Organisation / Federation | Legal and constitutional standing | Is the organisation legally and constitutionally established and current? | Confirm registration, constitution, affiliations and required filings. | Governance improvement should start from a valid legal and constitutional base. | Registration, constitution, affiliation certificate, AGM records
ORG-02 | Context | Sport Organisation / Federation | Board effectiveness | Is the board or governing committee functioning effectively and meeting its responsibilities? | Review board composition, meeting regularity, decisions and conflicts of interest. | A functioning governing body is central to credibility and accountability. | Board minutes, attendance, skills matrix, conflict declarations
ORG-03 | Context | Sport Organisation / Federation | Membership and affiliates | Is the membership or affiliated-club base current, active and understood? | Verify active members, clubs, regions and participation trends. | Services and representation should reflect the real active membership base. | Membership register, club affiliations, regional records
ORG-04 | Context | Sport Organisation / Federation | Competition and programme delivery | Are core competitions and participation programmes delivered reliably? | Review the annual calendar, completion rates and participant experience. | Core delivery performance should guide future expansion. | Competition calendar, entries, completion reports, participant feedback
ORG-05 | Context | Sport Organisation / Federation | Coaches and officials | Is there an adequate pipeline of trained coaches, officials and technical personnel? | Map current accredited personnel and priority gaps. | Technical workforce capacity can limit participation and performance growth. | Accreditation records, course records, workforce register
ORG-06 | Context | Sport Organisation / Federation | Athlete pathway | Is there a clear and workable pathway from participation to higher performance? | Map pathway stages, selection, support and progression evidence. | Athlete development should connect grassroots activity to realistic performance opportunities. | Pathway framework, squads, selection criteria, athlete tracking
ORG-07 | Context | Sport Organisation / Federation | Financial management | Are budgeting, financial controls and reporting sufficiently reliable? | Review budget, approvals, bank controls and financial reporting. | Financial credibility is essential for grants, sponsors and member trust. | Budget, statements, audit, approval procedures
ORG-08 | Context | Sport Organisation / Federation | Member service and communication | Are communication and services meeting the needs of members and affiliates? | Identify the most important information and services members require. | Member trust depends on timely, clear and useful communication. | Website/social media, notices, service standards, member feedback
ORG-09 | Context | Sport Organisation / Federation | Partnerships and revenue | Are partnerships, sponsorships and funding relationships sufficiently developed? | Map current partners, funding concentration and realistic new opportunities. | Diversified relationships reduce dependence on a single funding source. | Sponsor agreements, grants, partner MOUs, revenue mix
ORG-10 | Context | Sport Organisation / Federation | Integrity and safeguarding | Are integrity, safeguarding, disciplinary and complaint systems fit for purpose? | Confirm minimum policies, responsible officers and reporting pathways. | Governance credibility requires safe, fair and transparent sport. | Safeguarding policy, complaint process, disciplinary rules, integrity policies
CLB-01 | Context | Community Sport Club | Committee and governance | Is the club committee active, representative and clear about its responsibilities? | Confirm committee roles, meeting arrangements and basic governance requirements. | Simple, active governance is more valuable than complicated structures that are not used. | Committee list, constitution, meeting records
CLB-02 | Context | Community Sport Club | Membership and participation | Is the club's active participant base known and sufficiently stable? | Count active participants by relevant age, gender and programme groups. | Club planning should start from real participation rather than nominal membership. | Membership list, attendance, registration data
CLB-03 | Context | Community Sport Club | Coaches and volunteers | Are enough coaches, volunteers and helpers available for regular delivery? | Identify minimum delivery roles and gaps. | Volunteer capacity usually determines how much activity a community club can sustain. | Volunteer register, coach list, roster
CLB-04 | Context | Community Sport Club | Regular programme | Is there a reliable and attractive schedule of training, games or activities? | Review frequency, attendance and cancellations. | Consistency is essential for member retention and community trust. | Programme calendar, attendance, cancellation records
CLB-05 | Context | Community Sport Club | Facility access | Does the club have reliable access to suitable and safe places to operate? | Confirm access conditions, times, costs and responsibilities. | Programme growth is constrained if facility access is uncertain. | Booking agreement, venue schedule, access permission
CLB-06 | Context | Community Sport Club | Equipment | Is there enough safe and serviceable equipment for current activities? | Inventory essential equipment and identify the minimum replacement need. | Equipment priorities should follow actual participation and safety needs. | Inventory, condition check, equipment issue register
CLB-07 | Context | Community Sport Club | Club finances | Can the club meet basic operating costs without creating barriers to participation? | Review fees, recurring costs, cash position and likely funding sources. | Financial sustainability must be balanced with affordability. | Cashbook, fees, budget, grant records
CLB-08 | Context | Community Sport Club | Inclusion and safeguarding | Are children, women, people with disability and other participants able to participate safely and fairly? | Check safeguarding, inclusion barriers and responsible-person arrangements. | Community legitimacy depends on safe and inclusive participation. | Safeguarding procedure, inclusion policy, accessibility check
CLB-09 | Context | Community Sport Club | Community partnerships | Does the club have useful relationships with schools, community leaders and local organisations? | Identify 3–5 relationships that could directly improve participation or delivery. | Local partnerships can provide facilities, volunteers, participants and legitimacy. | School agreements, community contacts, local sponsor support
CLB-10 | Context | Community Sport Club | Retention and sustainability | Is the club retaining participants and developing future leaders? | Track attendance, retention, volunteers and young leaders over time. | Long-term sustainability depends on retaining people, not only recruiting them. | Retention data, volunteer progression, leadership succession
GOV-01 | Context | Government Sport Department / Agency | Mandate and statutory role | Is the department's sport mandate and division of responsibilities clear? | Confirm statutory responsibilities, delegated functions and overlaps with other agencies. | Clear mandate reduces duplication and improves accountability for public sport services. | Legislation, regulation, organisational mandate, delegations
GOV-02 | Context | Government Sport Department / Agency | Policy and strategic alignment | Are programmes and investments aligned with current government priorities and plans? | Map major activities to approved policy and planning documents. | Public resources should be traceable to agreed priorities and outcomes. | RPJMD/Renstra, national policy, annual work plan
GOV-03 | Context | Government Sport Department / Agency | Budget and resource allocation | Are budgets allocated transparently to priority services, facilities and programmes? | Compare allocations, execution and service priorities. | Budget structure should reveal whether stated priorities are actually resourced. | Budget, DPA, expenditure reports, programme allocations
GOV-04 | Context | Government Sport Department / Agency | Workforce capability | Does the department have the staffing and technical capability required for its mandate? | Map positions, vacancies, technical skills and priority capability gaps. | Workforce capacity should match programme, facility and governance responsibilities. | Staff establishment, vacancy list, competency profile
GOV-05 | Context | Government Sport Department / Agency | Programme delivery | Are public sport programmes delivered consistently and reaching intended groups? | Review programme completion, reach, participation and service quality. | Delivery evidence should drive continuation, redesign or discontinuation. | Programme reports, beneficiary data, attendance, evaluation
GOV-06 | Context | Government Sport Department / Agency | Facility and asset oversight | Is there effective oversight of public sport facilities and equipment? | Map facilities, operators, condition, use, maintenance and accountability. | Asset oversight should distinguish ownership, operation and service performance. | Asset register, condition reports, utilisation data, operator agreements
GOV-07 | Context | Government Sport Department / Agency | Grants and funding administration | Are grants, subsidies and support programmes transparent, timely and linked to outcomes? | Review criteria, approvals, acquittals and performance reporting. | Funding administration should reward clear public value and accountable delivery. | Grant guidelines, recipient list, acquittals, performance reports
GOV-08 | Context | Government Sport Department / Agency | Coordination and partnerships | Is coordination with districts, sport bodies, schools and other agencies effective? | Identify overlapping responsibilities and priority coordination mechanisms. | Fragmented public delivery can waste resources and confuse stakeholders. | MOUs, coordination forums, joint plans, stakeholder map
GOV-09 | Context | Government Sport Department / Agency | Monitoring and data | Does the department have reliable data for participation, facilities, programmes and funding? | Identify the minimum management dashboard and data owners. | Better decisions require a small set of consistent and trusted management data. | MIS, facility data, participation reports, budget performance
GOV-10 | Context | Government Sport Department / Agency | Public accountability and compliance | Are procurement, reporting, audit, public information and integrity requirements effectively managed? | Review recent audit, procurement, reporting and complaint issues. | Public-sector sport management must combine service performance with compliance and integrity. | Audit findings, procurement records, public reports, complaints
PRG-01 | Context | Sport Programme / Project | Outcomes and target group | Are the intended outcomes and target participants clearly defined? | Confirm who the programme is for and what should change as a result. | Delivery and evaluation should be organised around a small number of clear outcomes. | Programme design, logic model, target group definition
PRG-02 | Context | Sport Programme / Project | Delivery model | Is the delivery model practical for the available time, locations and participants? | Review frequency, duration, locations and delivery method. | A realistic delivery model is more important than an ambitious but unworkable design. | Session plan, delivery calendar, venue plan
PRG-03 | Context | Sport Programme / Project | Reach and participation | Is the programme reaching the intended number and type of participants? | Compare target and actual participation and identify access barriers. | Low reach or the wrong participant mix should trigger redesign before expansion. | Registration, attendance, demographic data
PRG-04 | Context | Sport Programme / Project | Delivery workforce | Are enough capable staff, coaches or facilitators available? | Confirm roles, workload, technical capability and supervision. | Programme scale should reflect the real delivery workforce. | Staff roster, coach qualifications, facilitator list
PRG-05 | Context | Sport Programme / Project | Venues and equipment | Are venues and equipment adequate, safe and accessible for delivery? | Check venue availability, equipment gaps and safety requirements. | Delivery quality depends on reliable access to essential physical resources. | Venue bookings, equipment list, safety check
PRG-06 | Context | Sport Programme / Project | Budget and cost | Is the programme affordable and are the major costs understood? | Compare essential costs with confirmed funding and in-kind support. | A minimum viable delivery model should be clear before adding optional costs. | Budget, cost per participant, funding agreement
PRG-07 | Context | Sport Programme / Project | Partners | Are the right organisations contributing participants, expertise, venues or funding? | Clarify partner roles and commitments. | Partnerships should reduce delivery gaps rather than create coordination burden. | Partner agreements, referrals, in-kind commitments
PRG-08 | Context | Sport Programme / Project | Inclusion and safeguarding | Is participation safe, inclusive and appropriate for the target group? | Check safeguarding, accessibility, gender and cultural barriers. | Participation outcomes are weakened when access or safety barriers are ignored. | Safeguarding, inclusion plan, accessibility check
PRG-09 | Context | Sport Programme / Project | Monitoring and evaluation | Are outputs and outcomes being measured simply and consistently? | Select a small set of measures and establish baseline and review points. | Monitoring should support decisions, not become a separate administrative project. | Attendance, pre/post measures, feedback, progress report
PRG-10 | Context | Sport Programme / Project | Sustainability and scale | Is there a realistic pathway to continue, improve or scale the programme? | Identify what must be sustained and what evidence would justify expansion. | Scale should follow demonstrated value and delivery capacity. | Continuation funding, partner commitment, evaluation results
EVT-01 | Context | Event / Competition | Governance and roles | Are event authority, decision-making and operational roles clearly assigned? | Confirm event owner, competition manager, venue leads and escalation process. | Clear event command reduces delay and confusion during delivery. | Event structure, delegations, responsibility chart
EVT-02 | Context | Event / Competition | Entries and eligibility | Are participant, team, classification and eligibility arrangements under control? | Confirm entry status, eligibility rules and outstanding issues. | Competition integrity starts with accurate and controlled entry information. | Entry list, eligibility rules, accreditation data
EVT-03 | Context | Event / Competition | Venue readiness | Are venues, fields of play and support spaces ready for the required competition standard? | Complete venue readiness checks and record outstanding defects. | Venue readiness should be verified against the actual competition requirement. | Venue checklist, field-of-play inspection, room plan
EVT-04 | Context | Event / Competition | Competition schedule and system | Is the draw, schedule and result-management system reliable and understood? | Test competition format, timetable, result entry and tie-breaking rules. | The competition system should be simple enough to operate correctly under pressure. | Draw, fixtures, competition regulations, result system test
EVT-05 | Context | Event / Competition | Officials and workforce | Are sufficient qualified officials, volunteers and operational staff confirmed? | Finalise roster, briefing and backup arrangements. | Workforce shortages can undermine an otherwise ready event. | Officials list, volunteer roster, briefing plan
EVT-06 | Context | Event / Competition | Safety, medical and emergency | Are medical, emergency, safeguarding and incident arrangements ready? | Confirm emergency plan, medical coverage and incident reporting. | Safety arrangements are non-negotiable event readiness conditions. | Emergency plan, medical roster, safeguarding procedure
EVT-07 | Context | Event / Competition | Logistics and equipment | Are competition equipment, transport, storage, communications and logistics ready? | Check critical equipment and logistics by venue and day. | Event reliability depends on a small number of critical logistics working every time. | Equipment checklist, transport plan, radios, storage
EVT-08 | Context | Event / Competition | Budget and procurement | Are event costs, procurement and financial controls under control? | Review committed cost, remaining procurement and contingency. | Late procurement and unclear cost control create avoidable event risk. | Event budget, purchase orders, procurement tracker
EVT-09 | Context | Event / Competition | Participant communication | Are teams, officials, spectators and stakeholders receiving clear and timely information? | Confirm the information calendar, responsible channel and urgent-contact process. | Clear communication reduces operational problems and participant dissatisfaction. | Bulletins, team handbook, contact list, website/social media
EVT-10 | Context | Event / Competition | Post-event reporting and legacy | Is there a practical plan to close the event, report results and capture lessons? | Define close-out reporting, asset return and lessons review. | Post-event review converts one event into improved future capability. | Final report template, asset return list, debrief plan
GEN-01 | Context | General / Other | Institutional environment | Are political, institutional and decision-making conditions sufficiently supportive? | Identify the authorities and institutional relationships that most affect delivery. | Institutional constraints and enablers should be made explicit before strategy is chosen. | Policy environment, approvals, institutional map
GEN-02 | Context | General / Other | Economic and funding environment | Are economic, funding and cost conditions manageable? | Identify the main financial pressures and realistic sources of support. | Strategy should reflect the real resource environment rather than assumed funding. | Budget trends, funding sources, cost pressures
GEN-03 | Context | General / Other | Social and community environment | Are community expectations, demographics and social conditions understood? | Identify the groups most affected and any participation or legitimacy issues. | Social conditions can change both demand and the acceptability of proposed actions. | Demographic data, consultation, social trends
GEN-04 | Context | General / Other | Technology and information | Are available technologies and information systems appropriate and reliable? | Identify essential technology, connectivity and information gaps. | Technology should simplify delivery and reporting, not create dependence on specialist systems. | Connectivity, systems inventory, digital capability
GEN-05 | Context | General / Other | Legal and regulatory environment | Are the relevant legal and regulatory requirements understood and manageable? | Identify required approvals, obligations and areas of uncertainty. | Legal and regulatory requirements should be treated as constraints or gates where necessary. | Legislation, regulations, permits, legal advice
GEN-06 | Context | General / Other | Physical and environmental conditions | Are location, infrastructure, climate, security or environmental conditions manageable? | Verify the physical conditions most likely to affect delivery. | Physical constraints can materially change cost, timing and feasibility. | Site information, transport, climate, security, infrastructure
GEN-07 | Context | General / Other | Partnership environment | Are useful partners available and willing to contribute? | Identify partners with a clear reason and capacity to participate. | Partnerships should provide defined value, not simply increase stakeholder numbers. | Partner map, commitments, MOUs
GEN-08 | Context | General / Other | Reputation and trust | Is there sufficient stakeholder trust and organisational credibility? | Identify significant trust, communication or reputation issues. | Low trust can undermine technically sound plans and should be addressed explicitly. | Feedback, complaints, media, stakeholder sentiment
GEN-09 | Context | General / Other | Emerging opportunities | Are there credible new opportunities that should influence the situation analysis? | Record only opportunities supported by a plausible pathway or evidence. | Opportunities should be distinguished from aspirations without an implementation pathway. | New policy, funding, partnerships, technology, demand trends
GEN-10 | Context | General / Other | External threats | Are the most important external threats and dependencies understood? | Identify the few threats that could materially change feasibility or performance. | High-consequence dependencies should be visible before strategic choices are made. | Funding dependency, policy change, security, climate, competition

## Data Bank (hidden)
TECHNICAL REFERENCE — STR-02 DATA BANK
No user input is required here. The Data Check sheet shows 10 indicators for the selected context.
ID | Context | Area | Indicator | Unit | Suggested next collection action | Context | Start Index
FD-01 | Sport Facility | Facility | Usable activity spaces | Number | Inspect each space and record usable / restricted / unavailable. | Sport Facility | 1
FD-02 | Sport Facility | Safety | Documented safety clearances completed | Number or % | Create one safety and compliance checklist. | Sport Organisation / Federation | 11
FD-03 | Sport Facility | Utilities | Essential utilities and amenities operational | % | Check power, water, sanitation, lighting and access. | Community Sport Club | 21
FD-04 | Sport Facility | Assets | Equipment items usable and approved for use | Number | Complete inventory, condition and custody check. | Government Sport Department / Agency | 31
FD-05 | Sport Facility | Maintenance | Critical maintenance defects outstanding | Number | Create a short critical-defect list and responsible owner. | Sport Programme / Project | 41
FD-06 | Sport Facility | People | Paid staff available for operation | Number | Confirm minimum staffing allocation. | Event / Competition | 51
FD-07 | Sport Facility | People | Active volunteers / casual helpers available | Number | Create a simple volunteer register and roster. | General / Other | 61
FD-08 | Sport Facility | Programmes | Active sport / recreation programmes | Number | Confirm first-stage programme calendar.
FD-09 | Sport Facility | Demand | Verified regular users / participants | Number | Complete a simple demand and user check.
FD-10 | Sport Facility | Finance | Minimum monthly operating cash requirement | Currency / month | Prepare a minimum-cash operating estimate.
OD-01 | Sport Organisation / Federation | Membership | Active registered members / affiliates | Number | Clean and verify the current membership register.
OD-02 | Sport Organisation / Federation | Governance | Board / committee positions currently filled | Number or % | Confirm current office holders and vacancies.
OD-03 | Sport Organisation / Federation | Governance | Required governance policies current | Number or % | List minimum required policies and review dates.
OD-04 | Sport Organisation / Federation | Delivery | Competitions / core programmes delivered in last 12 months | Number | Verify calendar delivery and cancellations.
OD-05 | Sport Organisation / Federation | Technical workforce | Accredited active coaches and officials | Number | Update technical workforce register.
OD-06 | Sport Organisation / Federation | Athlete pathway | Athletes in recognised development / performance pathway | Number | Create a basic pathway participant register.
OD-07 | Sport Organisation / Federation | People | Active volunteers supporting delivery | Number | Confirm volunteer roles and retention.
OD-08 | Sport Organisation / Federation | Finance | Annual operating revenue | Currency / year | Confirm latest actual revenue and major sources.
OD-09 | Sport Organisation / Federation | Partnerships | Active funding / delivery partners | Number | Record current partner contributions and expiry dates.
OD-10 | Sport Organisation / Federation | Compliance | Required reports / filings completed on time | % | List annual compliance requirements and due dates.
CD-01 | Community Sport Club | Participation | Active members / participants | Number | Verify current active participants, not historical registrations.
CD-02 | Community Sport Club | Governance | Committee roles filled | Number or % | Confirm committee positions and vacancies.
CD-03 | Community Sport Club | Delivery | Regular sessions / activities per week | Number | Confirm current operating timetable.
CD-04 | Community Sport Club | People | Active coaches / leaders | Number | Confirm regular delivery personnel.
CD-05 | Community Sport Club | People | Active volunteers / helpers | Number | Create a simple volunteer list and roster.
CD-06 | Community Sport Club | Facility | Reliable facility access hours per week | Hours | Confirm access agreement and actual available times.
CD-07 | Community Sport Club | Equipment | Essential equipment usable | % | Inventory essential equipment and urgent gaps.
CD-08 | Community Sport Club | Finance | Average monthly operating cost | Currency / month | Estimate recurring minimum cost.
CD-09 | Community Sport Club | Partnerships | Active community / school partners | Number | Identify partners making a practical contribution.
CD-10 | Community Sport Club | Retention | Participant retention / regular attendance | % | Track attendance or renewal over an agreed period.
GD-01 | Government Sport Department / Agency | Workforce | Approved positions currently filled | Number or % | Compare establishment with filled positions.
GD-02 | Government Sport Department / Agency | Finance | Annual sport budget allocated | Currency / year | Confirm current approved budget.
GD-03 | Government Sport Department / Agency | Finance | Budget execution / absorption | % | Compare actual expenditure with approved budget.
GD-04 | Government Sport Department / Agency | Programmes | Active public sport programmes | Number | List current funded programmes and status.
GD-05 | Government Sport Department / Agency | Facilities | Public sport facilities under oversight | Number | Update facility ownership / operator / condition register.
GD-06 | Government Sport Department / Agency | Grants | Sport grants / subsidies administered annually | Number / value | Confirm recipients, amounts and acquittal status.
GD-07 | Government Sport Department / Agency | Policy | Current policy / strategy actions on track | % | Link programme actions to approved strategic plan.
GD-08 | Government Sport Department / Agency | Coordination | Active inter-agency / district delivery partnerships | Number | Record active coordination mechanisms and responsibilities.
GD-09 | Government Sport Department / Agency | Reach | Verified participants / beneficiaries reached annually | Number | Standardise programme reach reporting.
GD-10 | Government Sport Department / Agency | Reporting | Required management / public reports submitted on time | % | Create a simple reporting calendar and ownership list.
PD-01 | Sport Programme / Project | Reach | Target participants | Number | Confirm current approved target.
PD-02 | Sport Programme / Project | Reach | Participants enrolled / reached | Number | Maintain current participant register.
PD-03 | Sport Programme / Project | Delivery | Planned sessions / activities completed | % | Compare planned and delivered sessions.
PD-04 | Sport Programme / Project | People | Active delivery staff / coaches | Number | Confirm current delivery roster.
PD-05 | Sport Programme / Project | Locations | Active delivery locations | Number | Confirm venue access and activity status.
PD-06 | Sport Programme / Project | Finance | Approved programme budget | Currency | Confirm approved budget and remaining funds.
PD-07 | Sport Programme / Project | Partnerships | Active delivery partners | Number | Record partner role and contribution.
PD-08 | Sport Programme / Project | Attendance | Average attendance / retention | % | Track participation consistency.
PD-09 | Sport Programme / Project | Outputs | Planned outputs completed | % | Update simple output tracker.
PD-10 | Sport Programme / Project | Monitoring | Required monitoring / evaluation reports completed | % | Confirm review points and reporting dates.
ED-01 | Event / Competition | Entries | Confirmed teams / participants | Number | Finalise entry and eligibility list.
ED-02 | Event / Competition | Venues | Competition venues ready | Number or % | Complete venue readiness checks.
ED-03 | Event / Competition | Officials | Officials confirmed | Number or % | Finalise officials roster and backups.
ED-04 | Event / Competition | Workforce | Operational staff / volunteers confirmed | Number or % | Finalise event workforce roster.
ED-05 | Event / Competition | Safety | Required safety / medical approvals completed | Number or % | Complete event safety checklist.
ED-06 | Event / Competition | Finance | Event budget secured / committed | % | Confirm remaining funding and procurement exposure.
ED-07 | Event / Competition | Competition system | Fixtures / schedule complete | % | Test draw, timetable and result procedures.
ED-08 | Event / Competition | Logistics | Critical equipment / logistics items ready | % | Complete critical logistics checklist.
ED-09 | Event / Competition | Communication | Participant information issued | % | Confirm handbook, bulletins and contact channels.
ED-10 | Event / Competition | Close-out | Post-event reporting / debrief plan ready | Yes / No or % | Assign final-report and debrief responsibilities.
XD-01 | General / Other | People | People available for core delivery | Number | Identify the minimum workforce required.
XD-02 | General / Other | Finance | Available operating resources / budget | Currency | Confirm essential resource position.
XD-03 | General / Other | Stakeholders | Key stakeholders actively engaged | Number | Identify the stakeholders essential to progress.
XD-04 | General / Other | Delivery | Active services / activities | Number | Confirm what is actually being delivered now.
XD-05 | General / Other | Reach | Verified users / beneficiaries | Number | Establish a simple current service baseline.
XD-06 | General / Other | Systems | Essential processes operating reliably | % | Identify only the processes critical to delivery.
XD-07 | General / Other | Risk | High-consequence unresolved risks | Number | Create a short critical-risk list.
XD-08 | General / Other | Evidence | Priority management data currently available | % | Identify missing data that changes decisions.
XD-09 | General / Other | Partnerships | Active partner commitments | Number | Verify practical partner contributions.
XD-10 | General / Other | Approvals | Critical approvals / decisions completed | % | List outstanding approvals and accountable owner.