## HOME
STR-04 — STRATEGIC IMPLEMENTATION & OPERATIONAL PLAN
Purpose: convert agreed strategy into specific implementation actions, responsibilities, milestones and management follow-up.
Subject / Entity |  |  | Active Strategies | 0
Plan / Initiative |  |  | Active Actions | 0
Location / Community |  |  | Complete Actions | 0
Responsible Body |  |  | Blocked Actions | 0
Planning Period |  |  | Overdue Actions | 0
Implementation Notes |  |  | Implementation Status | Load adopted STR-03 strategies
IMPLEMENTATION CONTEXT
Context Type | Sport Organisation / Federation |  | Minimum Initial Input | Paste / enter the selected STR-03 strategic responses
Planning Stage | Reactivation / Recovery |  | Action Generation | 5 context-sensitive implementation actions per active strategy
Maximum Strategic Responses | 5 |  | Ongoing Management Input | Owner, dates, status, resources and blocker / progress note
QUICK START
1 | Choose Context | Select the same operating context used in STR-02 and STR-03.
2 | Bring Forward Strategy | On Strategy Inputs, paste up to five adopted or develop-further strategic responses from STR-03.
3 | Review Generated Actions | Operational Plan creates five context-sensitive implementation actions for each active strategy.
4 | Manage Delivery | Add action owner, start / due dates, status, resource note and blocker / progress note as implementation proceeds.
5 | Report | Use the Dashboard and Management Summary for routine management review.
IMPLEMENTATION PRINCIPLES
Principle | What STR-04 does |  |  | What STR-04 deliberately avoids
Strategy to action | Breaks each strategic response into five practical implementation phases. |  |  | Another strategic assessment | STR-04 assumes strategic choices have already been made in STR-03.
Context first | Changes the implementation action wording for facilities, organisations, clubs, government, programmes and events. |  |  | A 200-line project plan | Maximum design is 5 strategies × 5 actions.
Milestones | Provides a suggested output and measure for every generated action. |  |  | Inventing factual evidence | Owners, dates, resources and blockers remain management inputs.
Management control | Tracks status, overdue actions and blockers. |  |  | False precision | Dates and costs are optional until management can set them responsibly.
Implementation discipline | Highlights the next unfinished milestone for each strategy. |  |  | Replacing judgement | Generated actions are editable starting points.
Review cycle | Supports routine implementation review and improvement. |  |  | Strategy on the shelf | The tool is designed to be used during delivery, not only during planning.
Implementation rule: if more than five strategic responses appear necessary, consolidate related responses before building the operational plan.

## Strategy Inputs
STR-04 — STRATEGY INPUTS FROM STR-03
Bring forward up to five strategic responses selected in STR-03. Strategic Response is the only essential field; the other fields improve the operational output.
Priority | Strategy ID | Strategic Response | Strategic Theme | Indicative Lead | Planning Horizon | Decision | Gate Status | Active? (Auto) | Implementation Warning (Auto)
1 | [7 empty] | No
2 | [7 empty] | No
3 | [7 empty] | No
4 | [7 empty] | No
5 | [7 empty] | No
Practical rule: carry forward only strategic responses that management genuinely intends to implement. Operational housekeeping should not be promoted into a strategic priority simply because it is useful.

## Operational Plan
STR-04 — OPERATIONAL PLAN
Five implementation actions are generated for each active strategy. Grey cells are automatic. Yellow cells are management inputs used during implementation.
Action ID | Strategy Priority | Strategy ID | Strategic Theme | Strategic Response | Phase | Suggested Action (Auto) | Edited Action (Optional) | Working Action (Auto) | Output / Milestone (Auto) | Measure / Evidence (Auto) | Suggested Lead | Action Owner | Suggested Timing | Start Date | Due Date | Status | Resource / Cost Note | Blocker / Progress Note | Due Status (Auto)
Use the suggested action as a starting point. Edit only where the wording needs to reflect local reality. The management fields can be completed progressively as implementation becomes concrete.
Formulas:
Due Status (Auto) = IF([Action ID]="","",IF([Status]="Complete","Complete",IF([Status]="Blocked","Blocked",IF([Status]="On Hold","On Hold",IF(AND([Due Date]<>"",[Due Date]<TODAY()),"Overdue","Open")))))

## Implementation Dashboard
STR-04 — IMPLEMENTATION DASHBOARD
Context: Sport Organisation / Federation ¦ Subject: Not entered
KPI | Result |  | Management Indicator | Result
Active Strategies | 0 |  | Completion Rate
Active Actions | 0 |  | Strategies Complete | 0
Complete | 0 |  | Strategies Blocked | 0
In Progress | 0 |  | Gate Warnings | 0
Not Started | 0 |  | Actions With Owner | 0
Blocked | 0 |  | Actions With Due Date | 0
Overdue | 0 |  | Overall Status | Load strategies
IMPLEMENTATION BY STRATEGY
Priority | Strategy ID | Strategic Theme | Strategic Response | Actions | Complete | Completion % | Status | Overdue | Blocked
1 |  |  |  | 0 | 0 |  |  | 0 | 0
2 |  |  |  | 0 | 0 |  |  | 0 | 0
3 |  |  |  | 0 | 0 |  |  | 0 | 0
4 |  |  |  | 0 | 0 |  |  | 0 | 0
5 |  |  |  | 0 | 0 |  |  | 0 | 0
IMPLEMENTATION ATTENTION
Check | Current Result | Management Meaning
Blocked actions | 0 | Resolve blockers before adding more activity.
Overdue actions | 0 | Confirm whether timing, ownership or scope needs correction.
Gate warnings | 0 | Do not allow planning gates to disappear simply because implementation has started.
Actions without owner | 0 | Every active action should eventually have one accountable owner.
Actions without due date | 0 | Dates can remain blank early, but should be added once delivery is genuinely scheduled.

## Management Summary
STR-04 — MANAGEMENT IMPLEMENTATION SUMMARY
One-page implementation view: strategic response, status, next milestone, accountable lead and blocker.
Subject / Entity |  |  | Complete Actions | 0
Context | Sport Organisation / Federation |  | Blocked Actions | 0
Planning Period |  |  | Overdue Actions | 0
Active Strategies | 0 |  | Gate Warnings | 0
Active Actions | 0 |  | Implementation Status | Load strategies
Completion Rate |  |  | Management Focus | Load adopted strategies
STRATEGIC IMPLEMENTATION STATUS
Priority | Strategy ID | Strategic Response | Theme | Lead / Owner | Horizon | Gate | Status | Next Milestone | Key Blocker / Note
1
2
3
4
5
MANAGEMENT REVIEW QUESTIONS
1 | What is blocked, and who can remove the blocker?
2 | Which next milestone matters most in the coming review period?
3 | Are owners, dates and resources now specific enough for the actions that have started?
4 | Have any implementation gates or assumptions changed since STR-03?
5 | What evidence shows that implementation is producing the intended result rather than just completing activity?
STR-04 is an implementation control tool, not a substitute for detailed project management. Add detail only when it helps delivery and accountability.

## Technical - Action Bank (hidden)
TECHNICAL REFERENCE — STR-04 CONTEXT ACTION BANK
No user input is required. The Operational Plan uses these context-sensitive five-phase implementation templates.
Key | Context | Phase | Phase Name | Action Template | Suggested Output / Milestone | Suggested Measure / Evidence | Suggested Timing | Context | Start Index
Sport Facility¦1 | Sport Facility | 1 | Confirm Preconditions | Confirm approvals, access, safety prerequisites and owner/operator responsibilities required to implement: {STRATEGY} | Authority and readiness requirements confirmed | Required approvals and critical prerequisites recorded | Immediate | Sport Facility | 1
Sport Facility¦2 | Sport Facility | 2 | Design Delivery | Translate the strategy into a simple facility / operating work plan with clear scope, sequence and minimum standards: {STRATEGY} | Facility / operating implementation plan | Work plan approved with scope, sequence and minimum standards | Immediate / early implementation | Sport Organisation / Federation | 6
Sport Facility¦3 | Sport Facility | 3 | Mobilise Resources | Assign the staff, contractors or volunteers, equipment, budget and partners required to implement: {STRATEGY} | Resources and responsibilities confirmed | Named owners and essential resources confirmed | Before delivery | Community Sport Club | 11
Sport Facility¦4 | Sport Facility | 4 | Implement | Implement the strategy in staged, manageable steps while protecting safety, assets and service continuity: {STRATEGY} | Implementation milestones delivered | Planned phase milestones completed | According to strategy horizon | Government Sport Department / Agency | 16
Sport Facility¦5 | Sport Facility | 5 | Monitor & Improve | Monitor facility use, condition, cost, participation and operating issues arising from the strategy and improve where required: {STRATEGY} | Implementation review and improvement actions | Performance evidence reviewed and corrective actions recorded | Ongoing / review cycle | Sport Programme / Project | 21
Sport Organisation / Federation¦1 | Sport Organisation / Federation | 1 | Confirm Preconditions | Confirm Board approval, governing authority, policy requirements and stakeholder roles required to implement: {STRATEGY} | Governance authority and responsibilities confirmed | Board / governing approval and accountable roles recorded | Immediate | Event / Competition | 26
Sport Organisation / Federation¦2 | Sport Organisation / Federation | 2 | Design Delivery | Translate the strategy into a practical policy, programme or organisational delivery plan: {STRATEGY} | Approved implementation / programme plan | Plan defines scope, standards, responsibilities and sequence | Immediate / early implementation | General / Other | 31
Sport Organisation / Federation¦3 | Sport Organisation / Federation | 3 | Mobilise Resources | Allocate people, budget and technical capability, and engage clubs, athletes, officials and partners needed to implement: {STRATEGY} | Delivery capacity and partner commitments confirmed | Required workforce, resources and partner roles confirmed | Before delivery
Sport Organisation / Federation¦4 | Sport Organisation / Federation | 4 | Implement | Launch and implement the strategy through the organisation's programme, competition or governance calendar: {STRATEGY} | Strategy implementation commenced | Planned implementation milestones delivered | According to strategy horizon
Sport Organisation / Federation¦5 | Sport Organisation / Federation | 5 | Monitor & Improve | Monitor participation, performance, governance, finance and compliance outcomes and improve the strategy where required: {STRATEGY} | Performance review and improvement actions | Key indicators reviewed and improvement actions recorded | Ongoing / review cycle
Community Sport Club¦1 | Community Sport Club | 1 | Confirm Preconditions | Confirm committee approval, member need, venue access and any safety or safeguarding requirements for: {STRATEGY} | Club approval and basic prerequisites confirmed | Committee decision and essential access / safety requirements recorded | Immediate
Community Sport Club¦2 | Community Sport Club | 2 | Design Delivery | Turn the strategy into a simple club delivery approach that members and volunteers can understand and use: {STRATEGY} | Simple club implementation plan | Activity scope, schedule and responsibilities agreed | Immediate / early implementation
Community Sport Club¦3 | Community Sport Club | 3 | Mobilise Resources | Secure the coaches, volunteers, equipment, venue time and basic finance needed to implement: {STRATEGY} | People and practical resources confirmed | Essential people, equipment, venue and finance confirmed | Before delivery
Community Sport Club¦4 | Community Sport Club | 4 | Implement | Commence the strategy through regular club activity and maintain simple operating records: {STRATEGY} | Club activity implemented | Planned sessions / actions commenced and recorded | According to strategy horizon
Community Sport Club¦5 | Community Sport Club | 5 | Monitor & Improve | Track attendance, retention, cost, safety issues and member feedback and make practical improvements: {STRATEGY} | Club review and improvement actions | Participation and delivery evidence reviewed and actions updated | Ongoing / review cycle
Government Sport Department / Agency¦1 | Government Sport Department / Agency | 1 | Confirm Preconditions | Confirm legal / policy mandate, responsible unit, approvals and public accountability requirements for: {STRATEGY} | Mandate, authority and accountable unit confirmed | Required approvals and responsible unit formally recorded | Immediate
Government Sport Department / Agency¦2 | Government Sport Department / Agency | 2 | Design Delivery | Translate the strategy into a practical policy, programme, guideline or service-delivery mechanism: {STRATEGY} | Approved implementation mechanism | Implementation model / guideline approved with clear responsibilities | Immediate / early implementation
Government Sport Department / Agency¦3 | Government Sport Department / Agency | 3 | Mobilise Resources | Secure budget, staffing, procurement, data and inter-agency coordination required to implement: {STRATEGY} | Government resources and coordination confirmed | Budget, staffing, procurement and partner responsibilities confirmed | Before delivery
Government Sport Department / Agency¦4 | Government Sport Department / Agency | 4 | Implement | Implement the strategy through the responsible programmes, facilities, grants or service units: {STRATEGY} | Public-sector implementation milestones delivered | Planned outputs delivered across responsible units / locations | According to strategy horizon
Government Sport Department / Agency¦5 | Government Sport Department / Agency | 5 | Monitor & Improve | Monitor delivery, expenditure, outputs, compliance and public value and adjust implementation where needed: {STRATEGY} | Management performance review | Performance, budget and compliance evidence reviewed and corrective actions recorded | Ongoing / review cycle
Sport Programme / Project¦1 | Sport Programme / Project | 1 | Confirm Preconditions | Confirm target outcomes, participant group, approvals, safeguarding requirements and partner roles for: {STRATEGY} | Programme prerequisites confirmed | Target group, outcomes, approvals and partner roles recorded | Immediate
Sport Programme / Project¦2 | Sport Programme / Project | 2 | Design Delivery | Translate the strategy into a practical delivery model, calendar, participation pathway and monitoring approach: {STRATEGY} | Programme implementation plan | Delivery model, schedule and measures approved | Immediate / early implementation
Sport Programme / Project¦3 | Sport Programme / Project | 3 | Mobilise Resources | Secure venues, delivery staff, equipment, funding and partner contributions needed to implement: {STRATEGY} | Programme delivery resources confirmed | Essential resources and delivery responsibilities confirmed | Before delivery
Sport Programme / Project¦4 | Sport Programme / Project | 4 | Implement | Deliver the strategy in staged programme cycles and maintain simple participant and delivery records: {STRATEGY} | Programme delivery commenced / completed | Planned programme milestones and sessions delivered | According to strategy horizon
Sport Programme / Project¦5 | Sport Programme / Project | 5 | Monitor & Improve | Monitor reach, attendance, participant experience and outcome measures and adapt the programme where needed: {STRATEGY} | Programme review and improvement actions | Participation and outcome evidence reviewed and actions updated | Ongoing / review cycle
Event / Competition¦1 | Event / Competition | 1 | Confirm Preconditions | Confirm event authority, competition regulations, entries, venue requirements and critical approvals for: {STRATEGY} | Event prerequisites confirmed | Authority, regulations, entries and critical approvals recorded | Immediate
Event / Competition¦2 | Event / Competition | 2 | Design Delivery | Translate the strategy into the relevant competition, venue, logistics, safety and communication plan: {STRATEGY} | Approved event implementation plan | Event plan defines schedule, standards, roles and contingencies | Immediate / early implementation
Event / Competition¦3 | Event / Competition | 3 | Mobilise Resources | Confirm officials, workforce, equipment, medical / safety, transport, procurement and budget needed to implement: {STRATEGY} | Event resources and workforce confirmed | Critical workforce, logistics, equipment and finance confirmed | Before delivery
Event / Competition¦4 | Event / Competition | 4 | Implement | Deliver the strategy through event operations and competition control according to the approved schedule: {STRATEGY} | Event implementation delivered | Required event / competition milestones completed | According to strategy horizon
Event / Competition¦5 | Event / Competition | 5 | Monitor & Improve | Close out results, finance, assets and incidents; conduct a debrief and record improvements for future events: {STRATEGY} | Event close-out and lessons report | Close-out completed and lessons / improvements recorded | Post-event review
General / Other¦1 | General / Other | 1 | Confirm Preconditions | Confirm authority, scope, requirements, stakeholders and critical dependencies required to implement: {STRATEGY} | Implementation prerequisites confirmed | Authority, requirements and dependencies recorded | Immediate
General / Other¦2 | General / Other | 2 | Design Delivery | Translate the strategy into a clear implementation approach with defined outputs and responsibilities: {STRATEGY} | Implementation plan | Scope, outputs, responsibilities and sequence agreed | Immediate / early implementation
General / Other¦3 | General / Other | 3 | Mobilise Resources | Assign the people, resources, budget and partners required to implement: {STRATEGY} | Resources and responsibilities confirmed | Essential owners and resources confirmed | Before delivery
General / Other¦4 | General / Other | 4 | Implement | Implement the strategy in manageable stages and record progress against milestones: {STRATEGY} | Implementation milestones delivered | Planned milestones completed | According to strategy horizon
General / Other¦5 | General / Other | 5 | Monitor & Improve | Monitor performance, issues and outcomes; review and improve implementation where required: {STRATEGY} | Implementation review and improvement actions | Performance evidence reviewed and actions updated | Ongoing / review cycle

## Technical - Automation
TECHNICAL AUTOMATION — NO USER INPUT REQUIRED
Expands each active STR-03 strategic response into five context-sensitive implementation phases.
Action ID | Strategy Slot | Strategy Priority | Strategy ID | Strategic Response | Theme | Suggested Lead | Strategy Horizon | Decision | Gate Status | Phase | Phase Name | Action Template | Suggested Action | Suggested Output | Suggested Measure | Suggested Timing | Active
| 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | No
| 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [6 empty] | No
| 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | [6 empty] | No
| 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [6 empty] | No
| 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [6 empty] | No
| 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | No
| 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [6 empty] | No
| 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | [6 empty] | No
| 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [6 empty] | No
| 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [6 empty] | No
| 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | No
| 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [6 empty] | No
| 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | [6 empty] | No
| 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [6 empty] | No
| 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [6 empty] | No
| 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | No
| 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [6 empty] | No
| 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | [6 empty] | No
| 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [6 empty] | No
| 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [6 empty] | No
| 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | No
| 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | [6 empty] | No
| 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | [6 empty] | No
| 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | [6 empty] | No
| 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | [6 empty] | No