## Project Brief
ISMT STR-05 — STRATEGIC ISSUE IMPLEMENTATION PROJECT PLAN
Purpose: take one important strategic issue or response and turn it into a practical, distributable project plan for the person responsible for delivery.
Project Title |  | Project Status | Not started | QUICK START
Strategic Issue / Challenge |  | Overall Progress |  | 1 | Define the project | Complete the yellow project fields. Project Type selects the implementation pathway.
Agreed Strategic Response / Project Direction |  | Actions Complete |  | 2 | Review the generated plan | Ten practical project actions appear automatically on Project Plan.
Desired Outcome |  | Actions In Progress |  | 3 | Edit only where needed | Suggested actions, outputs and measures are starting points; use the optional edit fields to localise them.
Context Type | Sport Facility | Blocked Actions |  | 4 | Assign delivery | Add Action Owner, Planned Start, Planned Due, Status, resources and dependencies as the plan becomes concrete.
Project Type | Facility / Asset | Overdue Actions |  | 5 | Manage the project | Update Status and Progress / Blocker Note during implementation reviews.
Strategic Theme |  | Next Milestone |  | 6 | Distribute / report | Project Brief, Project Plan and Management Summary can stand alone for the responsible lead.
Source / Reference |  | Current Management Focus
Responsible Lead |  |  |  | PROJECT DESIGN RULES
Project Sponsor / Authority |  |  |  | One issue | STR-05 deliberately handles one strategic issue / response in depth.
Project Start Date |  |  |  | Ten actions | The project is limited to ten implementation steps to keep ownership and review manageable.
Target Completion Date |  |  |  | Context + type | Context affects stakeholders; Project Type determines the implementation pathway.
Success Measure |  |  |  | No blank-page planning | Actions, milestones and evidence measures are drafted automatically.
|  |  |  | No false facts | People, dates, budget, dependencies and real progress remain management inputs.
|  |  |  | Standalone | The workbook can be distributed without requiring the recipient to understand STR-02/03/04.
KEY PROJECT DEPENDENCIES / CONDITIONS |  | AUTO PROJECT FOCUS
Dependency / Condition 1 |  | Project Focus
Dependency / Condition 2
Dependency / Condition 3
Dependency / Condition 4 |  | Typical Support | Asset owner / custodian; facility lead; technical / safety advisers; community / landowners; user groups
Implementation principle: the responsible lead should be able to open this workbook and understand the issue, the intended outcome, the ten-step pathway, the next milestone and any blocker without reopening the strategic-planning analysis.

## Project Plan
STR-05 — PROJECT IMPLEMENTATION PLAN
Project Type: Facility / Asset ¦ Context: Sport Facility ¦ Yellow cells are the project manager inputs.
Step | Phase | Suggested Action (Auto) | Edited Action (Optional) | Working Action (Auto) | Output / Milestone (Auto) | Measure / Evidence (Auto) | Suggested Lead | Action Owner | Typical Support (Auto) | Support / Partners | Suggested Timing | Planned Start | Planned Due | Status | Resource / Budget Note | Dependency / Decision | Progress / Blocker Note | Due Status (Auto)
1
2
3
4
5
6
7
8
9
10
Use the ten generated steps as the project backbone. Edit the action wording only where local circumstances require it; do not add detail unless it improves delivery, accountability or decision-making.
Formulas:
Due Status (Auto) = IF([Working Action (Auto)]="","",IF([Status]="Complete","Complete",IF([Status]="Blocked","Blocked",IF([Status]="On Hold","On Hold",IF([Planned Due]="","Unscheduled",IF([Planned Due]<TODAY(),"Overdue",IF([Planned Due]<=TODAY()+30,"Due Soon","Open")))))))

## Project Status
STR-05 — PROJECT STATUS
Project: Not entered ¦ Lead: Not assigned
KPI | Result |  | Current Control | Result
Overall Progress |  |  | Project Status | Not started
Complete |  |  | Current Phase
In Progress |  |  | Next Milestone
Not Started |  |  | Next Action
Blocked |  |  | Next Owner
On Hold |  |  | Next Due
Overdue |  |  | Current Blocker
Due Soon |  |  | Management Focus
Actions With Owner |  |  | Target Completion
10-STEP DELIVERY TRACKER
Step | Phase | Milestone | Owner | Due | Status | Due Status | Progress / Blocker Note
1
2
3
4
5
6
7
8
9
10
Management discipline: review blockers and overdue actions first, then confirm the next milestone, owner and due date. Avoid creating a separate action list outside this project plan.

## Management Summary
STR-05 — PROJECT MANAGEMENT SUMMARY
Standalone review sheet for the responsible lead and sponsor: project purpose, current status, next milestone, blocker and the ten-step delivery record.
Project Title |  |  | Project Status | Not started |  | Context | Sport Facility
Strategic Issue |  |  | Overall Progress |  |  | Project Type | Facility / Asset
Desired Outcome |  |  | Next Phase |  |  | Strategic Theme
Responsible Lead |  |  | Next Milestone |  |  | Source / Reference
Sponsor / Authority |  |  | Next Owner |  |  | Project Start
Target Completion |  |  | Current Blocker |  |  | Actions Complete
Success Measure |  |  | Management Focus |  |  | Overdue / Blocked
PROJECT DELIVERY STATUS
Step | Phase | Working Action | Output / Milestone | Owner | Planned Due | Status | Due Status | Resource / Budget | Progress / Blocker Note
1
2
3
4
5
6
7
8
9
10
PROJECT REVIEW QUESTIONS
1 | What is the single next milestone, and is one person clearly accountable for it?
2 | What is blocked or overdue, and what decision or resource is required to resolve it?
3 | Is the project still producing the intended strategic outcome, or only completing activity?
4 | When the project closes, who will own the ongoing system, policy, programme, asset or responsibility?

## Technical - Action Bank
TECHNICAL REFERENCE — STR-05 PROJECT ACTION BANK
No user input is required. Project Type selects the ten-step implementation pathway; Context supplies typical supporting stakeholders.
Project Type | Step | Phase | Action Template | Output / Milestone | Measure / Evidence | Suggested Timing | Project Type | Start Index | Typical Support | Context | Typical Support
Governance / Policy | 1 | Confirm | Confirm mandate, sponsor, decision authority and the governance / policy outcome required for: {ISSUE} | Mandate and decision authority confirmed | Sponsor, authority and intended governance outcome are recorded | Start-up | Governance / Policy | 1 |  | Sport Facility | Asset owner / custodian; facility lead; technical / safety advisers; community / landowners; user groups
Governance / Policy | 2 | Assess | Review the current governance arrangements, rules, evidence and gaps relevant to: {ISSUE} | Current-state governance review | Existing rules, evidence and material gaps are documented | Start-up | Facility / Asset | 11 |  | Sport Organisation / Federation | Board; executive / staff; member clubs / associations; athletes; coaches / officials; government / NOC / partners
Governance / Policy | 3 | Design | Develop the proposed governance, policy or structural solution required to address: {ISSUE} | Draft governance / policy solution | Draft solution clearly defines roles, rules, responsibilities and intended outcome | Early project | Programme / Participation | 21 |  | Community Sport Club | Committee; members; coaches / volunteers; venue owner; parents / community partners
Governance / Policy | 4 | Consult | Consult affected members, athletes, staff, government and other relevant stakeholders on the proposed solution | Stakeholder consultation completed | Key feedback, concerns and required changes are recorded | Early project | Workforce / Capability | 31 |  | Government Sport Department / Agency | Responsible unit; finance / procurement; legal / policy; districts / local government; sport bodies; service partners
Governance / Policy | 5 | Approve | Obtain the required Board, executive, government or member approval for the final governance / policy solution | Formal approval obtained | Approval decision and effective date are documented | Before implementation | Finance / Revenue | 41 |  | Sport Programme / Project | Programme lead; delivery staff / coaches; participants; venues; schools / clubs / community partners
Governance / Policy | 6 | Mobilise | Prepare the people, documents, communication, training and resources needed for implementation | Implementation readiness package | Responsibilities, documents, communication and resources are ready | Before implementation | Partnership / Stakeholder | 51 |  | Event / Competition | Event director; competition management; venue; officials; medical / safety / security; teams / participants; suppliers
Governance / Policy | 7 | Implement | Implement the approved governance / policy arrangements and communicate the changes to affected parties | Approved arrangements implemented | New governance / policy requirements are operating in practice | Implementation | Safety / Compliance | 61 |  | General / Other | Project sponsor; project lead; affected staff / users; technical advisers; finance / administration; external partners
Governance / Policy | 8 | Stabilise | Resolve early implementation issues and support people to apply the new arrangements consistently | Implementation stabilised | Initial implementation problems are resolved and responsibilities are functioning | Implementation | Data / Monitoring | 71
Governance / Policy | 9 | Monitor | Monitor compliance, decision quality, participation and intended governance outcomes | Governance performance review | Evidence shows whether the new arrangements are being applied and are effective | Review / close | Other | 81
Governance / Policy | 10 | Close / Embed | Close the project by confirming ongoing ownership, review dates and any remaining improvement actions | Project closed and governance embedded | Ongoing owner, review cycle and residual actions are confirmed | Review / close
Facility / Asset | 1 | Confirm | Confirm authority, access, ownership / custody, project sponsor and the required facility outcome for: {ISSUE} | Authority and facility project scope confirmed | Access, authority, custody and intended facility outcome are documented | Start-up
Facility / Asset | 2 | Assess | Complete the condition, safety, asset and serviceability assessment required to define the real scope of: {ISSUE} | Verified condition / readiness assessment | Priority defects, risks, usable assets and constraints are recorded | Start-up
Facility / Asset | 3 | Design | Define the minimum acceptable facility outcome, work scope, standards and implementation sequence | Facility work scope and standards | Required works, priorities, standards and sequence are agreed | Early project
Facility / Asset | 4 | Consult | Consult users, asset owner, technical advisers, community / landowners and other affected stakeholders | Stakeholder and user requirements confirmed | Critical access, use, technical and community requirements are recorded | Early project
Facility / Asset | 5 | Approve | Secure approvals, work authorisations, procurement decisions and budget / resource commitments required to proceed | Facility implementation approvals | Required approvals and resource commitments are confirmed | Before implementation
Facility / Asset | 6 | Mobilise | Mobilise contractors / workforce, materials, equipment, site controls and implementation logistics | Facility works mobilised | People, materials, equipment and site arrangements are ready | Before implementation
Facility / Asset | 7 | Implement | Deliver the priority works / asset actions needed to achieve the agreed facility outcome | Priority facility works completed | Specified work outputs are completed to the required standard | Implementation
Facility / Asset | 8 | Stabilise | Commission, test and progressively activate the facility / asset under controlled operating conditions | Facility / asset commissioned | Safety, utilities, equipment and operating readiness are verified | Implementation
Facility / Asset | 9 | Monitor | Monitor use, condition, maintenance, cost and operating problems and complete corrective actions | Early operating review | Condition, use and operating evidence are reviewed and corrective actions recorded | Review / close
Facility / Asset | 10 | Close / Embed | Close the project and transfer ongoing maintenance, custody and operating responsibilities into routine management | Facility project closed and handed over | Handover, maintenance ownership and outstanding actions are confirmed | Review / close
Programme / Participation | 1 | Confirm | Confirm the programme purpose, target group, sponsor, desired participation outcome and scope for: {ISSUE} | Programme purpose and target outcome confirmed | Target group, intended outcome, scope and accountable sponsor are recorded | Start-up
Programme / Participation | 2 | Assess | Establish the baseline demand, participation data, barriers and existing services relevant to: {ISSUE} | Participation baseline and needs summary | Current demand, barriers and service gaps are documented | Start-up
Programme / Participation | 3 | Design | Design the delivery model, participant pathway, schedule, locations and minimum programme standards | Programme delivery model | Delivery approach, schedule, locations and standards are documented | Early project
Programme / Participation | 4 | Consult | Consult target participants, coaches, clubs, schools, community groups and relevant delivery partners | Participant and partner consultation completed | Demand, access needs and partner commitments are recorded | Early project
Programme / Participation | 5 | Approve | Approve the programme model, safeguarding requirements, budget and performance measures | Programme approved for delivery | Delivery model, protections, budget and measures are approved | Before implementation
Programme / Participation | 6 | Mobilise | Secure venues, staff / coaches, equipment, funding, communication and partner support | Programme resources mobilised | Essential delivery resources and responsibilities are confirmed | Before implementation
Programme / Participation | 7 | Implement | Pilot or launch the programme and commence planned participant delivery | Programme delivery commenced | Planned sessions / activities are operating | Implementation
Programme / Participation | 8 | Stabilise | Stabilise delivery by resolving attendance, logistics, staffing and participant-experience issues | Programme delivery stabilised | Early delivery problems are resolved and participation is consistent | Implementation
Programme / Participation | 9 | Monitor | Monitor reach, attendance, retention, inclusion, cost and outcome measures | Programme performance review | Participation and outcome evidence is available and reviewed | Review / close
Programme / Participation | 10 | Close / Embed | Close the initial project phase and decide whether to continue, scale, redesign or embed the programme | Programme transition decision | Future delivery decision, ownership and improvement actions are confirmed | Review / close
Workforce / Capability | 1 | Confirm | Confirm the capability problem, accountable sponsor, affected roles and desired workforce outcome for: {ISSUE} | Workforce / capability issue defined | Affected roles, sponsor and target capability outcome are documented | Start-up
Workforce / Capability | 2 | Assess | Map current roles, staffing, skills, workload, gaps and existing capability evidence | Current workforce / capability profile | Current capacity and priority capability gaps are documented | Start-up
Workforce / Capability | 3 | Design | Design the target role structure, competency requirements, staffing model or development response | Target workforce / capability model | Required roles, competencies and development response are defined | Early project
Workforce / Capability | 4 | Consult | Consult affected staff, volunteers, managers, technical specialists and relevant stakeholders | Workforce consultation completed | Key concerns, implementation needs and role impacts are recorded | Early project
Workforce / Capability | 5 | Approve | Approve the workforce model, role changes, development approach and required resources | Workforce / capability response approved | Target structure / development plan and resource decisions are approved | Before implementation
Workforce / Capability | 6 | Mobilise | Mobilise recruitment, redeployment, training, induction, materials and supervisor support | Capability development resources ready | Required people, learning resources and support arrangements are in place | Before implementation
Workforce / Capability | 7 | Implement | Implement the agreed staffing, role, induction or capability-development actions | Workforce / capability actions implemented | Planned role and capability changes are operating | Implementation
Workforce / Capability | 8 | Stabilise | Support supervisors and participants to apply new roles, skills and operating expectations consistently | New capability stabilised | Early role / capability issues are resolved | Implementation
Workforce / Capability | 9 | Monitor | Monitor performance, workload, capability evidence and remaining gaps | Capability performance review | Evidence shows whether capability and delivery performance are improving | Review / close
Workforce / Capability | 10 | Close / Embed | Close the project by embedding induction, ongoing development, succession and review responsibilities | Capability project embedded | Ongoing ownership, development cycle and residual gaps are confirmed | Review / close
Finance / Revenue | 1 | Confirm | Confirm the financial issue, accountable sponsor, desired financial outcome and decision authority for: {ISSUE} | Financial project scope confirmed | Financial problem, target outcome, sponsor and decision authority are recorded | Start-up
Finance / Revenue | 2 | Assess | Establish the current cost, income, funding, cash-flow and financial-control baseline | Financial baseline | Reliable current financial position and material constraints are documented | Start-up
Finance / Revenue | 3 | Design | Develop realistic funding, revenue, cost-control or resource-allocation options | Financial options developed | Practical options, assumptions and expected financial effect are documented | Early project
Finance / Revenue | 4 | Consult | Consult affected managers, finance personnel, partners, sponsors or users on the feasible options | Financial stakeholder consultation completed | Key feasibility, affordability and stakeholder issues are recorded | Early project
Finance / Revenue | 5 | Approve | Select and approve the preferred financial model, controls, targets and implementation approach | Financial model approved | Approved model, controls, targets and responsibilities are documented | Before implementation
Finance / Revenue | 6 | Mobilise | Prepare systems, agreements, pricing / funding arrangements, controls and responsible staff | Financial implementation readiness | Required controls, agreements, systems and responsible roles are ready | Before implementation
Finance / Revenue | 7 | Implement | Launch the approved funding, revenue, cost or resource-allocation actions | Financial strategy implemented | Approved financial actions have commenced | Implementation
Finance / Revenue | 8 | Stabilise | Resolve early operational, collection, compliance, affordability or cash-flow issues | Financial implementation stabilised | Early financial operating problems are controlled | Implementation
Finance / Revenue | 9 | Monitor | Monitor income, expenditure, cash, variance, compliance and financial sustainability | Financial performance review | Financial performance is tracked against approved targets | Review / close
Finance / Revenue | 10 | Close / Embed | Close the project phase and embed the approved financial model into routine budgeting and reporting | Financial model embedded | Ongoing controls, ownership and review cycle are confirmed | Review / close
Partnership / Stakeholder | 1 | Confirm | Confirm the strategic partnership / stakeholder outcome, sponsor and authority required for: {ISSUE} | Partnership objective confirmed | Desired relationship outcome, sponsor and authority are recorded | Start-up
Partnership / Stakeholder | 2 | Assess | Map priority stakeholders, interests, influence, current relationships and mutual dependencies | Stakeholder map | Priority stakeholders, interests and relationship gaps are documented | Start-up
Partnership / Stakeholder | 3 | Design | Define the proposed value proposition, roles, contributions and preferred partnership model | Partnership proposition | Mutual value, roles and intended contributions are defined | Early project
Partnership / Stakeholder | 4 | Consult | Engage priority stakeholders and test interest, concerns, conditions and willingness to participate | Priority stakeholder engagement completed | Stakeholder positions, conditions and potential commitments are recorded | Early project
Partnership / Stakeholder | 5 | Approve | Negotiate and approve roles, contributions, governance arrangements and any formal agreement required | Partnership agreement / decision | Approved roles, contributions, decision arrangements and commitments are documented | Before implementation
Partnership / Stakeholder | 6 | Mobilise | Prepare joint work arrangements, contacts, resources, communication and implementation responsibilities | Partnership implementation ready | Joint responsibilities, resources and communication arrangements are confirmed | Before implementation
Partnership / Stakeholder | 7 | Implement | Commence joint delivery and fulfil the agreed early partnership commitments | Partnership activity commenced | Initial joint commitments are delivered | Implementation
Partnership / Stakeholder | 8 | Stabilise | Resolve coordination, communication, contribution or trust issues and stabilise the relationship | Partnership operating effectively | Early relationship and coordination issues are resolved | Implementation
Partnership / Stakeholder | 9 | Monitor | Monitor partner commitments, shared outputs, relationship quality and mutual value | Partnership performance review | Evidence shows whether commitments and shared value are being achieved | Review / close
Partnership / Stakeholder | 10 | Close / Embed | Review the partnership and decide whether to renew, expand, redesign or close the arrangement | Partnership review decision | Future relationship decision and ongoing responsibilities are confirmed | Review / close
Safety / Compliance | 1 | Confirm | Confirm the legal, regulatory, safety or safeguarding obligations, responsible authority and required outcome for: {ISSUE} | Compliance scope and authority confirmed | Applicable obligations, responsible authority and target outcome are documented | Start-up
Safety / Compliance | 2 | Assess | Audit current compliance, hazards, incidents, controls, records and material gaps | Compliance / safety baseline audit | Current controls and material compliance / safety gaps are documented | Start-up
Safety / Compliance | 3 | Design | Design the required policies, controls, procedures, reporting and corrective-action framework | Compliance control framework | Required controls and procedures are clearly defined | Early project
Safety / Compliance | 4 | Consult | Consult affected staff, participants, technical advisers, regulators and other relevant stakeholders | Compliance consultation completed | Operational implications and specialist requirements are recorded | Early project
Safety / Compliance | 5 | Approve | Approve required controls, responsibilities, resources and implementation priorities | Compliance actions approved | Controls, responsibilities, priorities and resources are authorised | Before implementation
Safety / Compliance | 6 | Mobilise | Prepare procedures, training, equipment, communication, registers and assurance arrangements | Compliance implementation ready | Required controls, training and evidence systems are ready | Before implementation
Safety / Compliance | 7 | Implement | Implement the required safety / compliance controls and corrective actions | Compliance controls implemented | Priority controls and corrective actions are operating | Implementation
Safety / Compliance | 8 | Stabilise | Test the controls through inspection, drill, review or practical assurance and correct failures | Controls tested and stabilised | Control effectiveness has been tested and failures corrected | Implementation
Safety / Compliance | 9 | Monitor | Monitor incidents, compliance records, assurance results and outstanding corrective actions | Compliance performance review | Compliance evidence and corrective actions are reviewed routinely | Review / close
Safety / Compliance | 10 | Close / Embed | Close the project by confirming ongoing compliance ownership, audit / review dates and residual actions | Compliance project embedded | Ongoing ownership, assurance cycle and residual actions are confirmed | Review / close
Data / Monitoring | 1 | Confirm | Confirm the management decision need, sponsor, users and required information outcome for: {ISSUE} | Information need confirmed | Decision need, users, sponsor and required information outcome are documented | Start-up
Data / Monitoring | 2 | Assess | Inventory current data sources, reporting practices, gaps, quality problems and information ownership | Current data / reporting baseline | Available data, gaps, quality and ownership are documented | Start-up
Data / Monitoring | 3 | Design | Define the indicators, definitions, collection standards, reporting frequency and minimum data set | Monitoring framework | Indicators, definitions and reporting requirements are agreed | Early project
Data / Monitoring | 4 | Consult | Consult data providers, users, managers and technical stakeholders on practicality and usefulness | Data-user consultation completed | Collection burden, usability and technical requirements are recorded | Early project
Data / Monitoring | 5 | Approve | Approve the monitoring framework, responsibilities, access rules and any required tools | Monitoring system approved | Measures, roles, access and tools are authorised | Before implementation
Data / Monitoring | 6 | Mobilise | Prepare templates / systems, assign data responsibilities and train users | Monitoring system ready | Tools, roles and user capability are in place | Before implementation
Data / Monitoring | 7 | Implement | Pilot and then operate the data collection, reporting and management-review process | Monitoring system operating | Required data is being collected and reported | Implementation
Data / Monitoring | 8 | Stabilise | Resolve data-quality, timeliness, usability and reporting problems and stabilise the process | Data process stabilised | Key data-quality and usability problems are controlled | Implementation
Data / Monitoring | 9 | Monitor | Review data quality, reporting compliance and evidence that the information is actually being used for decisions | Monitoring effectiveness review | Data quality and management use are reviewed | Review / close
Data / Monitoring | 10 | Close / Embed | Embed the monitoring cycle into routine management and confirm future system improvement actions | Monitoring system embedded | Ongoing ownership, reporting cycle and improvement actions are confirmed | Review / close
Other | 1 | Confirm | Confirm the issue, sponsor, authority, intended outcome and project boundaries for: {ISSUE} | Project scope confirmed | Issue, sponsor, authority, intended outcome and scope are recorded | Start-up
Other | 2 | Assess | Verify the current position, evidence, constraints and dependencies relevant to the issue | Current-state assessment | Material evidence, constraints and dependencies are documented | Start-up
Other | 3 | Design | Design the preferred solution and define the required outputs and standards | Proposed solution | Solution, outputs and standards are clearly defined | Early project
Other | 4 | Consult | Consult affected stakeholders and incorporate essential operational requirements | Stakeholder consultation completed | Key feedback and required changes are recorded | Early project
Other | 5 | Approve | Obtain the decisions, approvals and commitments required to proceed | Project approval | Required decisions, approvals and commitments are documented | Before implementation
Other | 6 | Mobilise | Mobilise the people, resources, systems and partners needed to implement | Implementation readiness | Essential resources and responsibilities are in place | Before implementation
Other | 7 | Implement | Implement the agreed solution in manageable stages | Implementation delivered | Planned implementation milestones are completed | Implementation
Other | 8 | Stabilise | Resolve early implementation issues and stabilise the new arrangements | Implementation stabilised | Early implementation problems are controlled | Implementation
Other | 9 | Monitor | Monitor progress, outcomes, risks and remaining actions | Performance review | Evidence shows progress against the intended outcome | Review / close
Other | 10 | Close / Embed | Close the project and transfer ongoing responsibilities into routine management | Project closed and embedded | Ongoing ownership, review cycle and residual actions are confirmed | Review / close